## Test Plan
Please click here for Book Shelf testplan full PDF.

## Mind Maps
Mind Map of BookShelf Web Application

## TestScenarios
Project Name | Book Shelf
Reference Document
Created By | Mir Mohaiminul Islam
Creation Date | 2025-02-27
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the functionality of "Sign In" feature
TS_002 |  | Validating the "Lost password" functionality
TS_003 |  | Validate the working of "Register" feature
TS_004 |  | Validate the "Search" functionality
TS_005 |  | Validate the "Filter" Functionality
TS_006 |  | Validate the "Product Order" functionality
TS_007 |  | Validate the "Account Details" functionality
TS_008 |  | Validate the "Shopping Cart" functionality
TS_009 |  | Validate the "Live Chat" functionality
TS_010 |  | Validate the "Contact" functionality
TS_011 |  | Validate the "logout" functionality

## TestCase
Product Name |  | Book Shelf | TC Start Date | 2025-03-01 | TC Execution Start Date | - - | [5 empty] | TEST CASE
Module Name |  | Payroll Percentage Contribution | TC End Date | 2025-03-12 | TC Execution End Date | - - |  |  |  |  | PASS | 116
Epic |  |  | Test Case Developed By | Mir Mohaiminul Islam | Browser (tested) | Yes |  |  |  |  | FAIL | 27
-4 |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | NO RUN | 7
-3 | [10 empty] | BLOCKED | 0
-2 | [10 empty] | TOTAL | 150
-1 | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
0 | Product Order | Browser Compatibility Testing | Account | Checkinging by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, , Mozilla Firefox, Microsoft Edge, Opera Mini |  |  |  | Passed
1
2 | User Authentication |  | Sign In | Verify the login screen will load after clicking on a "My Account" from header | Login Screen Should be appeear after clicking the "My Account" from header. | Found as expected | N/A |  |  |  | Passed
3 |  |  |  | Verify the alignment of displayed elements on the login screen should be compatible in cross browsers testing. | Displayed elements should be compitable in cross browser testing | Found as expected | N/A |  |  |  | Passed
4 |  |  |  | Verify that the login page of the application is responsive and aligns properly on different screen resolutions and devices | login papge should be responsive and support different screen resolutions and devices. | Found as expected | N/A |  |  |  | Passed
5 |  |  |  | Verify the login page title is correct or not. | Login page title should be correct. | Found as expected | N/A |  |  |  | Passed
6 |  |  |  | After the user login popup is open, the cursor should remain in the username text box by default | Cursor should remain in the username text box by default | Not found as expected | N/A | 1. Go to https://bookshelf.com.bd/ 2.click on my account from header. 3. sign in pop up will appear. | Bug Screenshot |  | Failed
7 |  |  |  | Check that the appropriate cursor is shown when hovering on login button. | Appropriate cursor shoulld be shown when hovering on login button. | Found as expected | N/A |  |  |  | Passed
8 |  |  |  | Verify that user can login with their account with valid credential | User should be logged in with their account with valid credential | Found as expected | N/A |  |  |  | Passed
9 |  |  |  | Checking that user will be redirected to the dashboard screen after login with the correct credential | User should be redirected to the dashboard screen after login with the correct credential | Not found as expected | Username:alt.d2-1mdlc5q Password: Eshrak#2052 | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. sign in pop up will appear. 4. provide username and password 5. Click on login button | Bug Screenshot |  | Failed
10 |  |  |  | Verify that user will get a correct confirmation message after successfull login attempt. | Confirmation message should be displayed top right corner of the website after a successful login attempt. | Not found as expected | Username:alt.d2-1mdlc5q Password: Eshrak#2052 | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. sign in pop up will appear. 4. provide username and password 5. Click on login button | Bug Screenshot |  | Failed
11 |  |  |  | Verify that the user can access all controls and elements by pressing the Tab key from the keyboard. | User should access all controls and elements by pressing the Tab key from the keyboard. | Found as expected | N/A |  |  |  | Passed
12 |  |  |  | Verify that user can login with their account with valid credential by pressing "EnterKey" | User should login with their account with valid credential by pressing "EnterKey" | Found as expected | N/A |  |  |  | Passed
13 |  |  |  | Verify that user can login with valid credential and clicking the login button | User should login with valid credential and clicking the login button | Found as expected | N/A |  |  |  | Passed
14 |  |  |  | Checking that whether an eye icon is added on the password filed or not | Eye icon should be present on the password file | Found as expected | N/A |  |  |  | Passed
15 |  |  |  | Verify that the eye icon of the password field properly working or not | Eye icon of the password field should be worked properly | Found as expected | N/A |  |  |  | Passed
16 |  |  |  | Verify that user can use valid "username" or "email address" for login | User should use valid "username" or "email address" for login | Found as expected | N/A |  |  |  | Passed
17 |  |  |  | Verify that the sign in form disappear when user pressed on close icon. | Sign in form should disappear when user pressed on close icon. | Found as expected | N/A |  |  |  | Passed
18 |  |  |  | Verify that Remember Me radio button properly working or not. | Remember Me button should be worked properly | Found as expected | N/A |  |  |  | Passed
19 |  |  |  | Verify the remember me checkbox should mark as checked after clicking on the label text and the check box. | Remember me checkbox should mark as checked after clicking on the label text and the check box. | Found as expected | N/A |  |  |  | Passed
20 |  |  |  | Checking that proper error message is displayed after entering the email address and leave the password field blank | Proper error message should be displayed after entering the email address and leave the password field blank | Found as expected | N/A |  |  |  | Passed
21 |  |  |  | Checking that the proper error message is displayed after entering password and leave the username or email field blank | Proper error message should be displayed after entering password and leave the username or email field blank | Found as expected | N/A |  |  |  | Passed
22 |  |  |  | Verify the error message is displayed after entering an invalid username. | Proper error message should be displayed after entering an invalid username | Found as expected | N/A |  |  |  | Passed
23 |  |  |  | Verify the error message should display after entering an invalid email format. | Proper error message should be displayed after entering an invalid email format | Not found as expected | Email:alt.d2-1mdlc5qyopmail.com | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. sign in pop up will appear. 4. provide invalid email address 5. Click on login button | Bug Screenshot |  | Failed
24 |  |  |  | Verify the displayed error message grammar is correct. | error message grammar should be correct | Found as expected | N/A |  |  |  | Passed
25 |  |  |  | Verify the displayed error message spell is correct. | error message spell should be correct | Found as expected | N/A |  |  |  | Passed
26 |  |  |  | Input Text of "username or email" will be disappear after unsuccessful Sign-In attempts | Input Text of "username or email" should be disappear after unsuccessful Sign-In attempts | Not found as expected | Email:alt.d2-1mdlc5qyopmail.com | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. sign in pop up will appear. 4. provide invalid email address and password 5. Click on login button 6.Check the error message | Bug Screenshot |  | Failed
27 |  |  |  | Check logged in user is not log out on closing the browser while login with checking the remember me radio button. | Logged in user should not be logged out on closing the browser. | Found as expected |  |  |  |  | Passed
28 |  |  |  | Verify logged-in user doesn’t redirected to login page by clicking the back button on the browsers tab. | Logged-in user should not be redirected to login page out by clicking the back button on the browsers tab | Not found as expected | Username:alt.d2-1mdlc5q Password: Eshrak#2052 | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. sign in pop up will appear. 4. provide username and password 5. Click on login button 6. Click the back button of the browser. | Bug Screenshot |  | Failed
29 |  |  |  | Verify the limit of unsuccessful attempts. Therefore, users cannot use brute force mechanisms to try all possible username-password combinations. | Login page should have limitations of log in attempts | Not found as expected | N/A | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. sign in pop up will appear. 4. provide invalid username and password 5. Click on login button 6. Repeat the process 5 times. | Bug Screenshot |  | Failed
30 |  |  |  | Verify that logged in user copy the url of the website and paste it in different browser and it redirect to login page | Logged in user should not be logged in with same session tokken with different browser. | Found as expected | N/A |  |  |  | Passed
31 |  |  |  | Checking that user can't visit login page by copy the url after logged in to website. | User should not be visited login page after logged in to website. | Found as expected | N/A |  |  |  | Passed
32 |  |  |  | Verify that username or email field rejects SQL injection attempts | Username or email field should reject SQL queries |  | N/A |  |  |  | Not Executed
33 |  |  |  | Verify that error message is shown for a specific field and in a specific position(under the field where error happen) | Error message should be shown for a specific field and in a specific position(under the field where error happen) | Not found as expected | N/A |  |  |  | Passed
34 | Logout |  | Logout | Verify user successfully Logout by clicking logout button | User should be logged out successfully and redirected to the login page | Found as expected | N/A |  |  |  | Passed
35 |  |  |  | Check that user will get a confirmation message after successful logout attempts. | user should be logged out successfully and get a confirmation message. | Not found as expected | N/A | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. sign in pop up will appear. 4. login with valid credential 5. click on logout button | Bug Screenshot |  | Failed
36 |  |  |  | Verify Logout Button Visibility | The "Logout" button should be clearly visible and accessible. | Found as expected | N/A |  |  |  | Passed
37 |  |  |  | Verify Logout from Multiple Devices | Only the logged-out device's session should end. | Found as expected | N/A |  |  |  | Passed
38 | User Registration |  | Register Account | Verifying by clicking on the "Register" button for blank input in Email address field. | Clicking the "Register" button with blank input should show an error message. | Found as expected | N/A |  |  |  | Passed
39 |  |  |  | Verifying all fields related to registration present on the registration form. | All required fields should be present on the registration form. | Found as expected | N/A |  |  |  | Passed
40 |  |  |  | Verifying password field should have validation for a minimum of 8 characters to maximum of 16 characters. | Password field should validate at least 8 characters. | Found as expected | N/A |  |  |  | Passed
41 |  |  |  | Verify that password field have validation for containing one special character, at least one uppercase character, and have a numerical. | password field should have validation for containing one special character, at least one uppercase character, and have a numerical. | Not found as expected | N/A |  |  |  | Passed
42 |  |  |  | Verifying password added by the user should be encrypted or not. | The password should be encrypted and displayed with asterisk symbol. | Found as expected | N/A |  |  |  | Passed
43 |  |  |  | Verifying whether the validation is added for the password and confirm whether passwords are the same or not. | Password validation should be applied, and the system should confirm if the passwords match. | Found as expected | N/A |  |  |  | Passed
44 |  |  |  | Verifying an eye icon added to the password and confirm the password field. | An eye icon should be present to toggle password visibility. | Found as expected | N/A |  |  |  | Passed
45 |  |  |  | Verifying that validation is added to the email field, only valid emails should be allowed to register successfully and redirected to dashboard. | The email field should validate that only valid emails can be registered. | Not found as expected(Redirect to dashboard without email verification) | Email: abc@gmail.com | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. go to register option 4. provide invalid email 5. Click on register button 6. It will redirect to dashboard without email validation | Bug Screenshot |  | Failed
46 |  |  |  | Verifying that the user adds blank spaces in email and clicks on the register button an error message should be shown. | An error message should be shown. | Found as expected | N/A |  |  |  | Passed
47 |  |  |  | Verify that error message is shown for a Email Address field and in a specific position(under the field where error happen) | Error message should be shown in a specific position(under the field where error happen) | Not found as expected | N/A |  |  |  | Passed
48 |  |  |  | Verifying that the user is not allowed to register an account with the same registered email by adding special character | Should not be able to register | Not found as expected | Email: abc#*@gmail.com | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. go to register option 4. provide email:abc#@gmail.com 5. Click on register button. | Bug Screenshot |  | Failed
49 |  |  |  | verify that user will not register with an already registered email address | Should not be able to register | Found as expected | N/A |  |  |  | Passed
50 |  |  |  | Verifying the email verification link was sent to the user's email address successfully. | The email verification link should be sent to the user's email successfully. | Found as expected | N/A |  |  |  | Passed
51 |  |  |  | Verifying the user is informed to check the spam folder if no email link is found in the inbox. | Should be informed to check the spam folder if the email link is not found in the inbox. | Not found as expected | Username:alt.d2-1mdlc5q Password: Eshrak#2052 | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. go to register option 4. provide email address 5. Click on register button 6. No notification shown about spam folder | Bug Screenshot |  | Failed
52 |  |  |  | Verifying Resend Link option is present if the user did not receive the link in the email. | A "Resend Link" option should be available if the user did not receive the email link. | Not found as expected | Username:alt.d2-1mdlc5q Password: Eshrak#2052 | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. go to register option 4. provide email address 5. Click on register button 6. no resend button or link exist | Bug Screenshot |  | Failed
53 |  |  |  | Verify captcha is added to the form or not in the registration form. | Captcha should be added | Not found as expected | N/A | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. go to register option 4. provide email address 5. Click on register button 6. no captcha exist | Bug Screenshot |  | Failed
54 |  |  |  | Verify example or dummy data shown as placeholder text in the email address field. | Placeholder should be shown in the email address field. | Found as expected | N/A |  |  |  | Passed
55 |  |  |  | Verify that user-added information is not removed from the fields in case of any validation fails. | User-added information should not be removed from the fields in case of any validation fails. | Found as expected | N/A |  |  |  | Passed
56 |  |  |  | Verify that the user is not allowed to register an account with the same registered email by adding plus for example useractual+1@gmail.com. | user should not be allowed to register an account with the same registered email by adding plus and should not be registered | Not found as expected | Email:abc+1@gmail.com | 1. Go to https://bookshelf.com.bd/ 2. click on my account from header. 3. go to register option 4. provide email:abc+1@gmail.com 5. Click on register button 6. It will redirect to dashboard without email validation | Bug Screenshot |  | Failed
57 |  |  |  | Verifying all spelling mistakes on the Register page. | Spelling should be correct. | Found as expected | N/A |  |  |  | Passed
58 | Product Search functionality |  | Search Bar | Verify that search bar input field is clearly visible in the website. | Search bar input field should be visible in the website. | Found as expected | N/A |  |  |  | Passed
59 |  |  |  | Verify whether placeholder text is added on search or not | placeholder text should be added on search | Found as expected | N/A |  |  |  | Passed
60 |  |  |  | Verify that the Search icon is clearly visible | Search icon should be visible | Found as expected | N/A |  |  |  | Passed
61 |  |  |  | Check that the appropriate cursor is shown when hovering on search icon button. | Appropriate cursor should be visible | Found as expected | N/A |  |  |  | Passed
62 |  |  |  | Verify search is functional and generating the correct result for correct keywords or not by adding a valid search | Correct result should be displayed fo valid keywords | Found as expected | N/A |  |  |  | Passed
63 |  |  |  | Verify the search is working by adding keywords and pressing the Enter key on the keyboard | Search bar should be working with Enter key from the keyboard | Found as expected | N/A |  |  |  | Passed
64 |  |  |  | Verify the search is working by adding keywords and on click on the search button | Search bar should be working with clicking the search button | Found as expected | N/A |  |  |  | Passed
65 |  |  |  | Verify if the user can paste the keyword with the mouse. | User should paste the keyword with the mouse | Found as expected | N/A |  |  |  | Passed
66 |  |  |  | Verify an error message displayed by entering invalid keywords in the search field and clicking the search button | Proper error message will be displayed with the invalid keyword | Found as expected | N/A |  |  |  | Passed
67 |  |  |  | Verify pagination added in case the search result goes on the number of pages | Pagination should be added in case the search result goes on the number of pages | Found as expected | N/A |  |  |  | Passed
68 |  |  |  | Verify whether pagination is accessible or not by clicking on the arrow icon and number | pagination should be accessible or not by clicking on the arrow icon and number | Found as expected | N/A |  |  |  | Passed
69 |  |  |  | Verify whether suggestions are shown or not on adding a keyword to the search. | Suggestions should be displayed under the search bar | Found as expected | N/A |  |  |  | Passed
70 |  |  |  | Verify the max and min range for the search keyword | Keyword range should be 8 to 50 characters | Not found as expected | Lorem ipsum dolor sit amet, consectetur adipiscing elit. Maecenas in neque quis orci imperdiet tincidunt. Curabitur non purus magna. Pellentesque habitant morbi tristique senectus et netus et malesuada fames ac turpis egestas. Donec eleifend tincidunt nibh eget consectetur. Cras eget auctor elit. Praesent gravida lorem id vulputate porttitor. Sed vitae dui ac dui volutpat auctor. Nullam sit amet lorem pharetra, posuere magna sit amet, convallis dui. Praesent posuere id ligula eget blandit. Cras nec est in mi iaculis faucibus ac fringilla risus. Cras accumsan dolor et ex scelerisque commodo. Etiam fringilla in turpis vel rutrum. Nullam tincidunt metus felis, ut blandit dui commodo id. Praesent et nibh eleifend, accumsan purus at, cursus justo. | 1. Go to https://bookshelf.com.bd/ 2. click on search bar. 3. write a long paragraph more than 50 characters 4. no fixed limit exist on that field | Bug Screenshot |  | Failed
71 | Filter Functionality(Price range) |  | Product Filter | Check the product Filter bar clearly visible or not. | Should able to visible clearly | Found as expected | N/A |  |  |  | Passed
72 |  |  |  | Verify that product can be filtered by clicking the filter icon | product should be filtered by clicking the filter icon | Found as expected | N/A |  |  |  | Passed
73 |  |  |  | Verify that Filter button text will be visible clearly after hovering the Filter button | Should be visible clearly after hovering the Filter button | Not Found as expected | N/A | 1. Go to https://bookshelf.com.bd/ 2. click on shop from menu bar of header 3. filter field will be visible there 4. Observing filter button when hovering. 5. After hovering the text of that button not seen | Bug Screenshot |  | Failed
74 |  |  |  | Verifying product rage can be selected properly | Should able to selected properly | Found as expected | N/A |  |  |  | Passed
75 |  |  |  | Verify the clear filter icon clearly visible | Icon should be clearly visible | Found as expected | N/A |  |  |  | Passed
76 |  |  |  | Verify that after clicking the clear filter button filtered product will be disappear and filter will be set as default. | Filter functionality should be set to default after clicking clear filter | Found as expected | N/A |  |  |  | Passed
77 | Password Reset |  | Forget password | Verifying that forget password link is present on the login screen | Forgot Password" link should be visible and clickable on the login screen. | Found as expected | N/A |  |  |  | Passed
78 |  |  |  | Verifying that on clicking on the forget password link forget password page should open. | Clicking "Forgot Password" should open the password recovery page. | Found as expected | N/A |  |  |  | Passed
79 |  |  |  | Verifying that the email field is present on the forget password page to recover the password. | Email field should be present on the "Forgot Password" page. | Found as expected | N/A |  |  |  | Passed
80 |  |  |  | Verifying as the user update password, the user should log out from all browser and devices. | Updating the password should log the user out from all browsers and devices. | Not found as expected | New Pass:Eshrak#2052 | 1. go to https://bookshelf.com.bd/ 2. login 3. change password from account details 4. user logged in after changing password | Bug Screenshot |  | Failed
81 |  |  |  | Verifying Reset Password button is present on the page. | Reset Password button should be present on the page. | Found as expected | N/A |  |  |  | Passed
82 |  |  |  | Verifying the whole button is clickable not only the button text. | The entire button, not just the text, should be clickable. | Found as expected | N/A |  |  |  | Passed
83 |  |  |  | Verifying the displayed error message for unregistered email address is meaningful. | Error message for unregistered users should be clear and informative. | Found as expected | N/A |  |  |  | Passed
84 |  |  |  | Verifying the confirmation message check your email to recover the password should be displayed after clicking on the button by entering the registered email id. | A confirmation message should appear to check the email for password recovery. | Found as expected | N/A |  |  |  | Passed
85 |  |  |  | Verifying that the user will get an email after entering a valid email id in forget password. | User should receive an email after entering a valid email ID in "Forgot Password." | Found as expected | N/A |  |  |  | Passed
86 |  |  |  | Verifying the email which the user gets against forgot password should be displayed in the inbox, not in the spam folder. | The password recovery email should appear in the inbox, not the spam folder. | Found as expected | N/A |  |  |  | Passed
87 |  |  |  | Verifying the user will get the forget password email from admin@demo.esouda.com. | The password recovery email should be sent from admin@demo.esouda.com | Found as expected | N/A |  |  |  | Passed
88 |  |  |  | Verifying the title exist or not of the forget password page. | The heading title should be "Forgot Password." | Found as expected | N/A |  |  |  | Passed
89 | Live Chat |  | Live chating fuctionality | Verify that Live chat icon is shown right bottom corner of the website | Live chat icon should be shown right bottom corner of the website | Found as expected | N/A |  |  |  | Passed
90 |  |  |  | Verify that clicking the "Live Chat" text functions correctly and redirects users to the chat interface. | Should be functioned correctly and redirects users to the chat interface. | Found as expected | N/A |  |  |  | Passed
91 |  |  |  | Verify that after clicking the chatting feature, the icon changes to a close icon | Should be changed to a close icon | Found as expected | N/A |  |  |  | Passed
92 |  |  |  | Verify that Close Icon properly works or not | Close Icon should work properly | Found as expected | N/A |  |  |  | Passed
93 |  |  |  | Verify that messenger chating option is working or not | should be worked properly | Found as expected | N/A |  |  |  | Passed
94 |  |  |  | Verify that user communicate through phone or not | should be worked properly | Found as expected | N/A |  |  |  | Passed
95 |  |  |  | Verify that whats app chating option is working or not | should be worked properly | Found as expected | N/A |  |  |  | Passed
96 | Account Deatails |  | User Profile | Verify that the "Account Details" page is displayed after selecting "Account Details" from the dropdown in the header. | Account details page should be appeared | Found as expected | N/A |  |  |  | Passed
97 |  |  |  | Verify the account details form with empty firstname field. | Proper error message should be displayed | Found as expected | N/A |  |  |  | Passed
98 |  |  |  | verify the account details form with empty lastname field. | Proper error message should be displayed | Found as expected | N/A |  |  |  | Passed
99 |  |  |  | Verify that the email address cannot be modified by the user in the Account Details section | Proper error message should be displayed | Not found as expected | Email:alt.d2-1mdlc5qabc@yopmail.com | 1. go to https://bookshelf.com.bd/ 2. login 3. change Email to "alt.d2-1mdlc5qabc@yopmail.com" 4. Click Submit. | Bug Screenshot |  | Failed
100 |  |  |  | Verify that the character limit of the firstname field is 50 character. | Character limit should be 50 | Not found as expected | Firstname: dgdfgdssssssssssssssssssssssssfgggggggggggggggggrrrrrrrrrrrrrrrrrrrrrrr | 1. go to https://bookshelf.com.bd/ 2. login 3. change Firstname to "dgdfgdssssssssssssssssssssssssfgggggggggggggggggrrrrrrrrrrrrrrrrrrrrrrr" 4. Click Submit. | Bug Screenshot |  | Failed
101 |  |  |  | Verify that the character limit of the last name field is 50 character. | Character limit should be 50 | Not found as expected | Lastname:ssssssssssssssssssssssssssssssssssseeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeewwwwwwwwwwwwwwwwwwwwwwwwwwwwkkkkkkkkkkkkkkkkkkkkkkkkkkkkkkkkkwwwwwwwwwwwwwwwwwwwllllllllllllllll | 1. go to https://bookshelf.com.bd/ 2. login 3. change lastname to "ssssssssssssssssssssssssssssssssssseeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeewwwwwwwwwwwwwwwwwwwwwwwwwwwwkkkkkkkkkkkkkkkkkkkkkkkkkkkkkkkkkwwwwwwwwwwwwwwwwwwwllllllllllllllll" 4. Click Submit. | Bug Screenshot |  | Failed
102 |  |  |  | Verify that the user can update profile information without filling in the Change Password fields. | User profile should be updated | Found as expected | N/A |  |  |  | Passed
103 |  |  |  | Verify that changing password redirect user to the login page | user should be redirected to the login page | Found as expected | N/A |  |  |  | Passed
104 |  |  |  | Check that a meaningful confirmation message displayed for a successful attempt of updating user profile | Confirmation message should be displayed. | Found as expected | N/A |  |  |  | Passed
105 |  |  |  | Verify that the user receives a professional error message when the New Password and Confirm Password fields do not match. | Error message should be displayed. | Not found as expected |  |  |  |  | Passed
106 |  |  |  | Verify that after changing username user can login with the new username and old password | user should be logged in. | Not found as expected | Username: Mohaiminul | 1. go to https://bookshelf.com.bd/ 2. login 3. change username to Mohaiminul" 4. Click Submit. | Bug Screenshot |  | Failed
107 |  |  |  | Verify that Error messages are grammertically correct or not | Should be correct | Not found as expected |  |  |  |  | Passed
108 |  |  |  | Verify that a professional and meaning placeholder is placed in each field of the Account details form | Placeholder should be present in each field. | Found as expected | N/A |  |  |  | Passed
109 | Contact Information |  | Contact | Verify that Location of the shop is marked with a location sign | Location of the shop should be marked with a location sign | Found as expected | N/A |  |  |  | Passed
110 |  |  |  | Verify the satelite view button working or not | Satelite button should be worked | Found as expected | N/A |  |  |  | Passed
111 |  |  |  | Verify the zoom in and zoom out icon working or not | Should be worked properly | Found as expected | N/A |  |  |  | Passed
112 |  |  |  | Verify Form Validation Messages for Empty Form Submission | Proper validation message should be displayed | Found as expected | N/A |  |  |  | Passed
113 |  |  |  | Check that meaningful placeholder is shown in every fields of contact form | Placeholder should be shown | Found as expected | N/A |  |  |  | Passed
114 |  |  |  | Verify that a valid confirmation message will be displayed for submitting a successful attempt. | Confirmation message should be displayed | Found as expected | N/A |  |  |  | Passed
115 |  |  |  | Check that the email address will be verified before submission the contact form. | email address should be verified | Not found as expected | Email:123@yahoo.com | 1. go to https://bookshelf.com.bd/ 2. login 3. go to contact form from header 4. change email to 123@yahoo.com" 4. Click Submit. | Bug Screenshot |  | Failed
116 |  |  |  | Verify that Error message is disappear within 5 second without reloading the website. | should be disappear within 5 second | Not found as expected | N/A | 1. go to https://bookshelf.com.bd/ 2. login 3. go to contact form from header 4. Give necessary credentials 4. Click Submit. | Bug Screenshot |  | Failed
117 |  |  |  | Verify that "Your Message" Field Does Not Execute SQL Queries | Should not run SQL Query. | [5 empty] | Not Executed
118 |  |  |  | Verify that the social media icon is properly working or not. | Should be worked properly | Found as expected | N/A |  |  |  | Passed
119 | Product Order |  | Product Order button | Verify the order button for each product is visible or not | Order Button Should be visible | Found as expected | N/A |  |  |  | Passed
120 |  |  |  | Verify the order button is clickable or not | Order Button Should be clickable | Found as expected | N/A |  |  |  | Passed
121 |  |  |  | Verify that after hovering the order button cart icon is visible or not | Should be visible after hovering | Found as expected | N/A |  |  |  | Passed
122 |  |  |  | Verify that clicking the order button it is redirected to checkout page or not | should be redirected to checkout page | Found as expected | N/A |  |  |  | Passed
123 |  |  | Checkout | Verify that correct product is added in checout page after clicking order button | Correct product should be displayed | Found as expected | N/A |  |  |  | Passed
124 |  |  |  | Verify that increasing the product quantity automatically update the product price in checkout page | Should be updated the product price automatically | Found as expected | N/A |  |  |  | Passed
125 |  |  |  | Verify that clicking the cross icon remove the existing product from the checkout page | cross icon should remove the existing product from the checkout page | Found as expected | N/A |  |  |  | Passed
126 |  |  |  | Verify that user can't be redirected checkout page without authentication. | Should not be redirected without authentication | Found as expected | N/A |  |  |  | Passed
127 |  |  |  | Check that "Out of order" product can't be displayed for checkout section. | "Out of order" product should not be displayed | [5 empty] | Not Executed
128 |  |  |  | Verify that apply coupon option is visible in check out page | coupon option should be visible in check out page | Found as expected | N/A |  |  |  | Passed
129 |  |  |  | Verify that user can add valid coupon for purchasing books | user should add valid coupon for purchasing books | [5 empty] | Not Executed
130 |  |  |  | Verify that user get a valid confirmation message after adding a coupon | User should get valid confirmation message | [5 empty] | Not Executed
131 |  |  |  | Verify Billing Information Form Submission with Empty fields. | User should get error message | Found as expected | N/A |  |  |  | Passed
132 |  |  |  | Verify that proper validation message is shown for "billing information" form field. | Proper validation message should be shown | Found as expected | N/A |  |  |  | Passed
133 |  |  |  | Verify the Name Field Character Limit (50 Characters) | Character limit should be 50 | Not found as expected | Name: lfsdkfhffffffffffffffffffffffffffffffffffffffffffffeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeerrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrwwwwwwwwwwwwwwwwwqqqqqqqqqqqqqqqqqqqqqqqqqq | 1. go to https://bookshelf.com.bd/ 2. login 3. go to Checkout page 4. Give name: "lfsdkfhffffffffffffffffffffffffffffffffffffffffffffeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeerrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrrwwwwwwwwwwwwwwwwwqqqqqqqqqqqqqqqqqqqqqqqqqq" | Bug Screenshot |  | Failed
134 |  |  |  | Verify That a User can not provide phone number more than 11 character | Character limit should be 11 | Not found as expected | Phone : "012545874558745221458745214" | 1. go to https://bookshelf.com.bd/ 2. login 3. go to Checkout page 4. Give phone: "l012545874558745221458745214" | Bug Screenshot |  | Failed
135 |  |  |  | Verify that after completing a valid purchase user recive a confirmation message for order completation | Confirmation message should be recieved | Found as expected | N/A |  |  |  | Passed
136 |  |  |  | Verify that the confirmation message have no spelling mistake | confirmation message should have no spelling mistake | Found as expected | N/A |  |  |  | Passed
137 |  |  |  | Verify that the confirmation message is grammertically correct. | confirmation message should be grammertically correct. | Found as expected | N/A |  |  |  | Passed
138 |  |  |  | Verify that the system does not save the shipping address for a second order | Should not save for the second order | Not found as expected |  |  |  |  | Not Executed
139 |  |  |  | Verify that clicking "Ship to a different address?" providing shipping information form or not. | Shipping information form should be shown | Found as expected | N/A |  |  |  | Passed
140 |  |  |  | Verify That Billing Information is not autofilled in the "shipping to another address" form | Should not be autofilled | Not found as expected |  |  |  |  | Not Executed
141 |  |  |  | Verify that proper error message shown for empty fields of shipping different address form. | Proper error message should be shown | Found as expected | N/A |  |  |  | Passed
142 | Shopping Cart |  | Shopping Cart | Verify the Shopping cart icon is visible or not | Should be visible | Found as expected | N/A |  |  |  | Passed
143 |  |  |  | Verify that clicking on shopping cart icon redirect user into shopping cart page | Clicking on shopping cart iconshould redirect user into shopping cart page | Found as expected | N/A |  |  |  | Passed
144 |  |  |  | Checking the Text of the "View Cart" Button on Hover | Button text should be visible when hovering | Not found as expected | N/A | 1. go to https://bookshelf.com.bd/ 2. login 3. go to Cart 4. Hover on "View Cart" button | Bug Screenshoot |  | Failed
145 |  |  |  | Verify that clicking on "view cart" button redirect user to cart page | Should be redirected to cart page | Not found as expected | N/A | 1. go to https://bookshelf.com.bd/ 2. login 3. go to Cart 4. Click on "View Cart" button | Bug Screenshoot |  | Failed
146 |  |  |  | Verify that clicking on "checkout" button redirect user to checkout page | Should be redirected to checkout page | Found as expected | N/A |  |  |  | Passed
147 |  |  |  | Check that "checkout" button is visible or not. | Checkout button should be visible | Found as expected | N/A |  |  |  | Passed
148 |  |  |  | Verify that the user can close the shopping cart popup using the "Esc" button | User should close the shopping cart popup using the "Esc" button | Found as expected | N/A |  |  |  | Passed
149 |  |  |  | Verify that user can remove product by clicking the cross icon(x) | User should remove product by clicking the cross icon(x) | Found as expected | N/A |  |  |  | Passed
150 |  |  |  | Verify that user can cancel shopping cart popup by clicking close(x) icon | user should cancel shopping cart popup by clicking close(x) icon | Found as expected | N/A |  |  |  | Passed
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [5 empty] | Result :
Project Name | Book Shelf
Module Name | Account,User authentication,User registration,Search, Filter product |  |  |  |  | Total No. | Status | New Features:- | Testing Scope:-
Feature Name | Register Account ,Account Login,Product order functionality, Search Functionality
Test Case Version | 1 |  |  |  |  | 116 | PASS
Written By | Mir Mohaiminul Islam |  |  |  |  | 27 | FAIL
Executed By | Mir Mohaiminul Islam |  |  |  |  | 7 | Not Executed
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Testing Environment : Google Chrome Browser
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 116 | 27 | 7 | 0 | 150
Grand Total | 116 | 27 | 7 | 0 | 150
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
#SL 01
Issue: The cursor is absnet in the username text box by default in the login popup
Reproducing Steps:
1. https://bookshelf.com.bd/
2. Click on my account from header.
3. sign in pop up will appear.
Env: Production
Module: Login
Priority: P1
Severity: Minor
Screenshot: Cursor error in login page
Expected: cursor should be present in the username text box by default in the login popup
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 02
Issue: User was not redirected to dashboard after successful login.
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. sign in pop up will appear.
4. provide username and password
5. Click on login button
Env: Production
Module: Login
Priority: P1
Severity: Critical
Screenshot: User was not redirect to dashboard
Expected: User should be redirected to dashboard after successful login.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 03
Issue: No confirmation message was shown after successful login
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. sign in pop up will appear.
4. provide username and password
5. Click on login button
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot: Confirmation_error
Expected: Confirmation message should be shown after successful login
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 04
Issue: No Error Message for invalid email format.
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. sign in pop up will appear.
4. provide invalid email address
5. Click on login button
Env: Production
Module: Login
Priority: P2
Severity: Major
Screenshot: invalid_email_error
Expected: Error Message should be shown for invalid email format
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 05
Issue: Username and password was not disappear after unsuccessful login
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. sign in pop up will appear.
4. provide invalid email address and password
5. Click on login button
6.Check the error message
Env: Production
Module: Login
Priority: P2
Severity: Critical
Screenshot: Username and password not dissapear error
Expected: Username and password should disappear after unsuccessful login
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 06
Issue: Logged-in user redirected to login page on clicking browser back button
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. sign in pop up will appear.
4. provide username and password
5. Click on login button
6. Click the back button of the browser.
Env: Production
Module: Login
Priority: P0
Severity: Critical
Bug Video: login page redirect issue
Expected: Logged in user should not redirected to login page
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 07
Issue: Login page allows unlimited login attempts
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. sign in pop up will appear.
4. provide invalid username and password
5. Click on login button
6. Repeat the process 5 times.
Env: Production
Module: Login
Priority: P0
Severity: Critical
Bug Video: login attempts issue
Expected: User should not allow to try more than 3 times to login with invalid credentials.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 08
Issue: Confirmation Message was not shown for logout
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. sign in pop up will appear.
4. login with valid credential
5. click on logout button
Module: Logout
Priority: P0
Severity: Major
Bug Video: Confirmation_Messege not shown
Expected: Confirmation Message should be shown when user logged out.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 09
Issue: The email field does not have email validation in the registration page.
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. go to register option
4. provide invalid email
5. Click on register button
6. It will redirect to dashboard without email validation
Env: Production
Module: Registration
Priority: P1
Severity: Major
Bug Video: Email_validation_error
Expected: Email address should be verified at the time of registration
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 10
Issue: User Registered an account by adding special character in existing email address
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. go to register option
4. provide email:'abc#@gmail.com' where the existing email is 'abc@gmail.com'
5. Click on register button
Env:
Module: Registration
Priority: P0
Severity: Critical
Bug Video: Adding Special Character in email
Expected: User should not register with existing email address
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 11
Issue: User was not got any alert message to check email in spam folder
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. go to register option
4. provide email address
5. click submit
Env: Production
Module: Registration
Priority: P2
Severity: Minor
Screenshot: Spam_issue
Expected: User should be got a notification for checking email in spam folder.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 12
Issue: Resend Email option was absent in Registration module.
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. go to register option
4. provide email address
5. Click on register button
6. no resend button or link exist
Env: Production
Module: Registration
Priority: P2
Severity: Minor
Screenshot: No Resend Link
Expected: Resend email option should be exist.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 13
Issue: Captcha option was not exist in registration form
Reproducing Steps:
1. Goto the URL http://localhost:1337
2. Click on the "Login" button in the right corner.
3. Enter password
Env: Production
Module: Registration
Priority: P2
Severity: Minor
Screenshot: Captcha not exist
Expected: Captcha option should be added in registration form.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 14
Issue: The user created a new registration using an existing email by appending '+1' to the address.
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on my account from header.
3. go to register option
4. provide email:abc+1@gmail.com
Env: Production
Module: Registration
Priority: P0
Severity: Critical
Bug Video: Email_issue_adding+1
Expected: User should not be procced to register with an existing email address with adding '+1'.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 15
Issue: Search Bar Allows Unlimited Input (Missing Character Limit)
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on search bar.
3. write a long paragraph more than 50 characters
Env: Production
Module: Search
Priority: P0
Severity: Major
Bug Video: Missing word limit_searchbar
Expected: Keyword range should be 8 to 50 characters
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 16
Issue: Filter button text disappear after hovering in filter module
Reproducing Steps:
1. Go to https://bookshelf.com.bd/
2. click on shop from menu bar of header
3. filter field will be visible there
4. Observing filter button when hovering.
5. After hovering the text of that button not seen
Env: Production
Module: Filter
Priority: P2
Severity: Minor
Bug Video: Filter button text disappear
Expected: Filter button text should be visible when hovering on it.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 17
Issue: User was not logged out from the website after updating the password
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change password from account details
4. user logged in after changing password
Env: Production
Module: Forget Password
Priority: P2
Severity: Minor
Bug Video: updating password Issue
Expected: User should logged out from all devices after changing password
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 18
Issue: Email Address was modified by logged in user
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change Email to "alt.d2-1mdlc5qabc@yopmail.com"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Critical
Bug Video: logged in user_ email modify issue
Expected: Logged in user should not modify email address.
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 19
Issue: Firstname field of user profile has no character limit.
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change Firstname to "dgdfgdssssssssssssssssssssssssfgggggggggggggggggrrrrrrrrrrrrrrrrrrrrrrr"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Major
Bug Video: No character limit in firstname
Expected: Maximum character limit should be 50
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 20
Issue: Lastname field of user profile has no character limit.
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change lastname to "ssssssssssssssssssssssssssssssssssseeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeee eewwwwwwwwwwwwwwwwwwwwwwwwwwwwkkkkkkkkkkkk kkkkkkkkkkkkkkkkkkkkkwwwwwwwwwwwwwwwwwwwllllllllllllllll"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Major
Bug Video: No character limit in lastname
Expected: Maximum character limit should be 50
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 21
Issue: User Unable to Log In After Updating Username
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change username to Mohaiminul"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Blocker
Bug Video: Username_update_issue
Expected: User should be able to login after updating username
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 22
Issue: User was able to enter invalid email address in the contact form
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. go to contact form from header
4. change email to 123@yahoo.com" which is an invalid email address.
4. Click Submit.
Env: Production
Module: Contact
Priority: P2
Severity: Minor
Bug Video: Contact_form_email_issue
Expected: Maximum character limit should be 50
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 20
Issue: Lastname field of user profile has no character limit.
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change lastname to "ssssssssssssssssssssssssssssssssssseeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeee eewwwwwwwwwwwwwwwwwwwwwwwwwwwwkkkkkkkkkkkk kkkkkkkkkkkkkkkkkkkkkwwwwwwwwwwwwwwwwwwwllllllllllllllll"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Major
Bug Video: No character limit in lastname
Expected: Maximum character limit should be 50
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 20
Issue: Lastname field of user profile has no character limit.
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change lastname to "ssssssssssssssssssssssssssssssssssseeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeee eewwwwwwwwwwwwwwwwwwwwwwwwwwwwkkkkkkkkkkkk kkkkkkkkkkkkkkkkkkkkkwwwwwwwwwwwwwwwwwwwllllllllllllllll"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Major
Bug Video: No character limit in lastname
Expected: Maximum character limit should be 50
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 20
Issue: Lastname field of user profile has no character limit.
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change lastname to "ssssssssssssssssssssssssssssssssssseeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeee eewwwwwwwwwwwwwwwwwwwwwwwwwwwwkkkkkkkkkkkk kkkkkkkkkkkkkkkkkkkkkwwwwwwwwwwwwwwwwwwwllllllllllllllll"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Major
Bug Video: No character limit in lastname
Expected: Maximum character limit should be 50
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 20
Issue: Lastname field of user profile has no character limit.
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change lastname to "ssssssssssssssssssssssssssssssssssseeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeee eewwwwwwwwwwwwwwwwwwwwwwwwwwwwkkkkkkkkkkkk kkkkkkkkkkkkkkkkkkkkkwwwwwwwwwwwwwwwwwwwllllllllllllllll"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Major
Bug Video: No character limit in lastname
Expected: Maximum character limit should be 50
Responsible QA: Mir Mohaiminul Islam
Bug Reporting
#SL 20
Issue: Lastname field of user profile has no character limit.
Reproducing Steps:
1. go to https://bookshelf.com.bd/
2. login
3. change lastname to "ssssssssssssssssssssssssssssssssssseeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeee eewwwwwwwwwwwwwwwwwwwwwwwwwwwwkkkkkkkkkkkk kkkkkkkkkkkkkkkkkkkkkwwwwwwwwwwwwwwwwwwwllllllllllllllll"
4. Click Submit.
Env: Production
Module: User Profile
Priority: P0
Severity: Major
Bug Video: No character limit in lastname
Expected: Maximum character limit should be 50
Responsible QA: Mir Mohaiminul Islam

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (82/82)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/82)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (66/82)*100 = 80.5%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (16/82)*100 = 19.5%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/82)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A